TERMS OF REFERENCE

FOR CONDUCTING BASELINE SURVEY FOR THE INCREASE PROJECT ORGANIC COTTON PRODUCTION

1.0 About SNV

The Netherlands Development Organization (SNV) is an international not-for-profit development organization that believes in contributing to poverty alleviation in Zambia through various programs/projects that it implements. There is great opportunity by all people to pursue their own sustainable development and SNV is working with different groups in pursuant of the same. SNV provides services in Agriculture, Water, Sanitation and Hygiene, and Renewable Energy. The recipients of these services include governmental institutions, non-governmental organizations and private sector organizations, communities, and individual households.

2.0 About the project

SNV is implementing the Increasing Climate Resilience in Energy & Agriculture Systems and Entrepreneurship (INCREASE) project. The project aims to address the major challenge of climate change that farmers, agribusinesses, and SMEs are facing. To achieve this the project will strengthen the adaptive capacity of agricultural and energy systems as well as the promotion of climate smart (CS) diversification practices and productive use of renewable energy (RE).

The INCREASE project has evolved from both lessons learned and achievements in two earlier Sida-funded projects on climate smart agriculture and renewable energy (biogas).

The project is being implemented for the period of three (3) years starting from January 2020 to 31st December 2022. It will cover Eastern, Central, Copper belt, Lusaka and Southern provinces, initially targeting to reach 11,300 small Holder farmers in cotton, dairy and horticulture value chains. The project aims at increasing the social, economic, environmental resilience and equity in agriculture and energy systems, through strengthening the adaptive capacity of agricultural and energy systems.

The project is promoting biogas and bioslurry as more relevant than ever for diversification of sustainable energy options and conservation type farming. Biogas and bioslurry have enormous growth potential in Zambia as hydrocarbons are being phased out, alternatives to wood fuel become more pressing and the agricultural sector is moving away from chemicals and more towards organic farming.

Organic cotton is cotton produced without the use of synthetic pesticides, fertilizers, growth regulators, hormones, defoliants, or any other chemicals that may affect the environmental ecosystem. It also seeks to maintain and replenish soil fertility and maintain the ecological balance for the environment where the crop is grown. Organic cotton fetches a higher wholesale market price compared to the conventional synthetic or inorganic cotton.

Under the cotton value chain the project is working with Alliance Ginnaries. The objective of the project is to partner with Alliance to facilitate cotton/soya farmers to get access to their cotton/soya and other food crops as well as to help farmers improve their livelihoods through capacity building in sustainable agricultural practices which will help them to increase their productivity while protecting the soil and the environment.

3.0 Objectives for the baseline study

The main objective of the baseline study is to set the benchmarks to ensure that the Organic Cotton (Pilot) Project contributes to improved organic cotton production for sustainable scale-up and farmer livelihoods. The following are the expected specific objectives of the baseline survey:

- To establish the status of the three proposed project sites in relation to the organic cotton project framework covering,

- Farmers’ capacity and knowledge levels to implement organic cotton farming,

- Farmer assets (household income, land use and current cotton practices)

Farmer access to market

- To ascertain current farmers experiences and competition with cotton farming in the area and document collective power to scale-up organic cotton farming as a viable option.

- To ascertain the relevance and sustainability of increased resilience to household change, land use and productivity among different cotton farmers

- To Identify the most important gender-related and social inclusion issues and establish how different gender related and social issues are expected to impact on the organic cotton project.

- Provide recommendations to the project and its partners for the project implementation and generate information for learning.

4.0 Approach and Methodology

The baseline survey is to be carried out in Lusaka province in Chongwe, Rufunsa and Luangwa districts by an independent consultant using a combination of qualitative and quantitative methods. The consultant is required to elaborate a solid baseline design and methodology as part of their work plan. The baseline design document should include a series of data collection instruments. In addition, the consultant will propose a Covid19 responsive approach to conducting the assignment adhering to the Government of Zambia and SNV’s measures to safeguard against contracting and spreading Covid19.

4.1 Data Collection Methodology

The consultant is expected to employ a variety of data collection and analysis techniques for both quantitative and qualitative data to ensure a comprehensive baseline exercise. This will likely include:

Secondary research: Data from Alliance Ginneries, relevant and recent (internet) research, data from the Ministry of Agriculture or other relevant government institutions. Data from the Cotton Board of Zambia and the Cotton Association of Zambia.

Surveys: Application of structured survey questionnaires with a representative, random sample of target population to quantitatively assess outcomes.

Focus Group Discussions: With target groups and other stakeholders to assess implementation experiences and effectiveness, document successes, challenges and lessons learned, and develop recommendations for improvement.

Key Informant Interviews: Consultations with value chain companies, SNV, SMEs, biogas enterprises (for the production of organic biofertilizer), input and output markets and other key project stakeholders. Guidance on appropriate stakeholders to engage during the exercise will be provided by field and SNV Country Office staff.

4.2 Sampling

. The consultant is expected to propose a representative sample size for the new districts in Lusaka province (Chongwe, Lufunsa and Lwangwa). The consultant will be expected to hire their own enumerators and hire their own transport to facilitate the smooth implementation of the assignment.

4.3 Data Analysis

Prior to the start of data collection, the evaluation team shall develop and present, for SNV review and approval, a data analysis plan that details how: (1) qualitative data such as key informant, stakeholder, and beneficiary interviews and/or focus group discussions will be transcribed and analysed; (2) how quantitative data will be analysed and presented. Whenever possible, data will be disaggregated and analysed by gender.

5.0 Deliverables

All written documents are to be submitted in English using Microsoft Word in both soft and hard copy. The main body of all reports should be written in simple, non-technical language (i.e. plain English), with any technical material to be presented in annexes. All primary data collected and analysis conducted for the purpose of the baseline will remain the property of SNV and must be submitted electronically and in a clear and comprehensible format in Microsoft Excel and Word.

1. Inception Report: which is 5 working days after signing the contract, a detailed report on the consultant’s proposed final baseline design and methodology will be submitted to SNV for approval. This will provide preliminary understanding based on document review, rationale and a detailed description of the methodology and tools, analytical methods, budget with a breakdown of costs and detailed work plan for the entire exercise. Any draft questionnaires or interview forms will also be submitted for review at this stage.

2. Interview Notes and List of Resource Documents: The Consultant shall provide SNV summaries of all key meetings, and discussions conducted during the course of the baseline and copies of any relevant documents and reports gathered during the baseline.

3. Summary Presentation of Findings to SNV and Stakeholders: The Consultant shall present initial findings to SNV and its stakeholders for review, comment and feedback. A PowerPoint presentation and handout shall be prepared for the presentation through a workshop to the project stakeholders preferably via online platform. The Consultant shall consider SNV and stakeholder comments and revise the draft report as appropriate.

4. Baseline Report: A draft baseline report is due within three business days of receiving SNV’s feedback to the draft report, one electronic (MS Word) copy of the final baseline report and the hard copy submitted to SNV. The final baseline report should not exceed 45 pages excluding annexes

6.0 Illustrative activity and Level of Effort (LOE) Matrix

The assignment is expected to be completed over a period of 35 calendar days - this period includes provision of all deliverables and travel time.

| Description | Total | Period |
| --- | --- | --- |
|  | Indicative days | d duration |
| Preparatory phase: Review of project documents and understanding the project contextual framework, designing of baseline tools and data collection and analysis methodology. Submission of the Inception Report, including sample size and data collection tools | 6 | week 1 |
| Field Work: Training of enumerators in the questionnaires and data collection including travel days | 16 | Week 2-3 |
| Analysis, report writing and submission of first draft report | 8 | week 4 |
| Baseline validation workshops (Preferably online) with SNV, SIDA and Stakeholders | 2 | Week 5 |
| Compilation and submission of Final report | 3 | Week 5 |
| Total | 35 |  |

7.0 Criteria for selection

A two-stage procedure shall be adopted in evaluating the proposals. The technical evaluation shall be carried out first, followed by the financial evaluation. The technical evaluation has 70% and financial proposal 30% weights. The evaluation items expectation and maximum score are presented in the table below.

| Evaluation Item | Expectation | Max Score |
| --- | --- | --- |
| Organizations/Consultant Experience | A brief of past relevant assignments (in similar regions) indicating scope, geographic coverage, staff involved, budget, and client (name and contacts). | 30 |
| Understanding of TOR and Proposed Approach and Methodology/Work Plan | Organizations perspective of what the assignment entails and the key considerations that should be made to implement it successfully. | 20 |
| Qualification & Experience of Staff | CV’s for nominated staff indicating their academic qualification and clear relevant experience summary | 20 |
| Financial Costs | A breakdown of costs detailing proposed staff days, daily rates, taxes and other direct costs related to the assignment in Zambia Kwacha using the attached template. The consultant is also expected to use their own transports and should include this in the direct costs as hired vehicles together with fuel. | Cost (30) |

8.0 Requirements of the consultant

The evaluation is to be done by a local consultant/firm with a team composition of individuals with a mix of expertise in Agriculture, Natural resources, Agribusiness, Climate change, Renewable Energy and Integrated Water Resources Management and experience in organic farming

Lead Consultant-Minimum of master’s degree level.  He/she should have strong experience in evaluation of agriculture, climate change and market support programmes as well as excellent analytical, communication, team management and communication skills (verbal and written). He/she should have 10 years of demonstrated experience in impact evaluations and practical experience in qualitative and quantitative research methodology, evaluation design and implementation. Experience in organic farming and cotton industry is an advantage.

Associate Consultants: Minimum of a degree in the relevant field. They should collectively have strong expertise in Agriculture, Climate Change, Renewable energy, Demography, Information technology. They should have good interpersonal skills, ability to work effectively as part of a team, good analytical and experience in the appropriate range of methodologies needed for the study.

9.0 Payment Terms

Payment plan shall be based on deliverables outlined upon successful and satisfactory completion of activities.  Therefore, the payment terms shall be as follows

- 40% initial payment – upon submission of inception report and its accompanying survey tools.

- 60% - final payment – Upon submission of final and accepted Baseline report

9.1 Invoices

Payment to the consultant will be based on the invoice submitted to SNV for the attention of Email: zambiatreasury@snv.org  Invoices will contain an itemized statement of the services performed and any expenses incurred.  The invoice shall be submitted in accordance with the current Scope of Work for this Agreement.

9.2 Manner of payment

Payment under this Agreement will be made by bank transfer to the consultant.

10.0 Submission of proposal:

Interested Consultants or firms are requested to submit:

- A technical proposal detailing their interpretation of the TOR, proposed methodology including sampling framework, work schedule and proposed budget.

- A capability statement demonstrating how they meet the required qualifications and competencies.

- Copies of all relevant Curriculum Vitae (CVs). Only CVs for the specific individuals that will form the proposed survey team should be included; two references (including one from your last client/employer).

All submissions should be sent via:

- Email to: Zambiaprocurement@snv.org the subject line should read ‘Baseline Survey (Organic Cotton Production) for INCREASE Project”

- Postal: Procurement Office, SNV Netherlands Development Organisation
7, Nkanchibaya Road, Rhodes Park, Lusaka, Zambia

Submissions are to be made available to SNV no later than 20 November 2021.