Terms of reference (ToR) for consultancy to provide the services of Print and electronic documentation, publicity of challenge fund and youth skilling and employment component of SUPREME project.

Project background

SNV is part of a consortium of 4 development organisations implementing the European Union funded Security, Protection and Economic Empowerment Program (SUPREME) in West Nile 4 districts of Uganda. The overall goal is to improve economic well-being for 25,000 refugees and host community members.

Project geographical coverage is 4 districts in West Nile and 12 sub counties i.e. Terego (Odupi, Omugo Uriama sub counties), Madi Okollo (Ewanga & Rigbo sub counties), Obongi (Itula, Gimara and Palorinya) and Moyo (Moyo, Lefori, Laropi and Metu Sub Counties).

- The project targets to benefit both host community and refugees at a ratio of 50% by each category. The refugees and host community will be targeted through community structures known as Savings and Development Clusters (SDCs)- being community groups formed and carrying activities including savings and lending, farming, and other group enterprises.

Specific Outcome: increased access to decent employment and economic opportunities for refugees and host communities.

Project Outputs

The project has 3 output areas:

Output 1: Financial inclusion and social cohesion among Savings and Development Clusters (SDCs) increased.

Output 2: Sustainable agricultural value chains and non-agricultural enterprises developed.

Output 3: Young women and men (aged 18-30 years) from SDC member households linked to private sector employment. Under output 3 of SUPREME project, SNV leads activities of skilling and creating employment opportunities for young men and women.

Purpose of the ToR

The purpose of this ToR is to seek the services of a suitable local service provider (individual (s) or company) to support and manage the SUPREME project team in managing and ensuring the print and electronic documentation of the SNV output 2 (challenge fund) and output 3 (youth skilling, mentorship and internship) activities including success stories writing, business profiling, Photography, videography, print media content, social media content, and coordinating internally and externally sharing of this content for visibility.

Specific Scope of activities for this ToR

- Develop together with project team the print and electronic (audio and visual) documentation plan for the project outputs.

- Professional development of business profiles of challenge fund grantees, identification of success stories and documentation electronically and print.

- Connect with the services of other related professional service providers for design, production and editing contents for print, visual (Photography, video clips), audio, and social media platforms.

- Undertake field visits and participate in identification, planning, of sites and subjects for documentation in line with SNV and EU communication guidelines.

- Other activities that may be related to the documentation of the project output activities

Expected output/deliverables:

The following outputs are expected from the consultant:

- 50 Challenge fund businesses profiles professionally developed (printable version)

- At least 10 Challenge fund success stories (related inclusive business) identified and documented (print and electronically) within the project period.

- 20 Success stories identified, developed and documented (print and electronically photographic and video) for youth skilling and employment program (5 on Skilling, 5 on mentorship, 5 on internship and 5 on employment)

- Successfully managed the process of execution, content, and quality of outputs (print and electronic documentation services) leveraged from other elated service providers

Duration of the Assignment and work planning.

The overall duration of this assignment is anticipated to be spread within a period of 1 year, but deliverables will have specific days spread across the contract period in phases as follows:

- Window one 30 Challenge fund business profiles documented with current state and the challenge funding ambitions (30 days)

- Window two 20 challenge fund business profiles documented and with current state and challenge funding ambitions (30 days)

- 10 success stories related to challenge fund documented in print and electronically and published on social media platforms and news papers (20 days)

- 20 print success stories identified and developed for youth who have been skilled and in employment. (30 days)

The consultant is expected draw work plans against the allocated days each time in agreement with the project implementation team and in consultant with the SNV communication consultant.

Desired Qualifications and experience

SNV SUPREME is looking for an individual consultant with the following qualifications:

- An individual consultant(s) or companies with CV qualifications in communications an/or marketing or development studies and proven experience

- Evidence of at least 5 years successfully implementing or delivering on communications or marketing assignment and outputs related to development projects or a project with a nexus of business and social development.

- Should have been in the field of development work and/or business over the last 10 years

- Possess a strong working knowledge of print and electronic material production and designs

- Proven skills in story writing and communicating in story form in both visual and print

- Self-motivated with development impact and good planner.

- Able to work with diverse teams and stakeholders especially at district level, refugees and host population.

- Experience with online and social media communication strategies and tech savvy,

- Possession of strong network in the media fraternity is an added advantage

Reporting

The selected service provider or consultant(S) shall report to SUPREME project Manager. Technically will work closely and be supported by both the Project technical Advisors on regular basis.

Submission requirements

The applicant should respond by submitting:

- An expression of interest with a detailed CV as proof of the required expertise for the terms of reference (TOR). The consultant should also submit a maximum of 5page proposition of he/she shall work with the project to deliver on the assignment outputs.

- Submit a proposal of expected professional fee (only) per day for executing this assignment.

- At least names of 3 referees from previous clients / similar assignments conducted

Additional information

Send to the above documents to ugandatenders@snv.org  by  23rd Dec 2021 5:00 pm EAT